## Overall Steps
Step | Pre-Work | Comments / Questions | Owner
1 | Check which scenarios & cubes have data for these accounts in OS PROD | Actuals under Ally_Consol and Ally_Total; to also re-load Ally_Expense | Katherine / Kristine
2 | Extract backup of journals for ALL periods | Extracted; Kristine to re-extract right before making updates | Kristine
3 | Complete backup of PROD application | PROD copy in progress | Kevin / Arindam / Katherine
4 | Obtain sign-off on group account list controlling if GL account is added to Detail or Planning | Group acct. list confirmed w/ Jeff | Katherine / Jeff
5 | Update account hierarchy table from step #5 in PROD | Table has been updated in PROD with new group acct. list | Katherine / Ethan
Step | Move Detail Accounts to Planning Accounts in PROD | Comments / Questions | Owner
1 | Create new parent account in DetailedActAccounts called To_Be_Deleted_GLAccts | To_Be_Deleted member already existing so changing the name | Kristine
2 | Remove relationship of 166 accounts to their current parent and move under To_Be_Deleted_GLAccts | To_Be_Deleted member already existing so changing the name | Kristine
3 | Rename 166 accounts by suffixing _old | E.g. 189030003 would be renamed as 189030003_old | Kristine
4 | Create 166 accounts as new members in PlanningAccounts structure | Using XML for metadata creation | Kristine
5 | Verify the updated account structure | Using AccountStructure_Check cube view in Consol cube view group | Kristine
6 | Verify the account properties | Using GridView in Dimension to check properties settings between the old and newly created members | Kristine
7 | Unlock the Consol Actual Data Load Workflows (where applicable) |  | Kristine
8 | Reload the Actuals Data for 2019M12 - 2022M5* | Dec. 2019 for consol ONLY; start at 2020 for Expense | Kristine
| Ally Consol (Manual) - Consol Actual Data Load |  | Kristine
Set integration parameter boolean to manual
| For PCA Connector, re-load the cube for each month. Can execute a bulk Workflow batch to "Load Cube" for all months in one year (see screenshot) | Do NOT retransform / revalidate as no change to the underlying data (very important for Dec. 2019)
| For PCA_Override_Connector, select the workflow step under each month and execute the "Load and Transform" step under Import. You will have to do this step from the Workflow by month but you can then complete the remaining Validate & Process steps using "Execute Batch" | PCA_Override_Connector data was cleared when we made update to process cube so can't just re-import.
| Ally Expense (Manual) - Actuals Load | *Dec. 2019 for consol ONLY; start at 2020 for Expense | Kristine
Set integration parameter boolean to manual
| Navigate to Ally_Expense --> Ally_Expenses_ACT Cube Root --> Actuals Load Workflow Profile Load. For Actuals load, re-load the cube for each month. Can execute a bulk worfklow batch to "Load Cube" for all months in one year. | Do NOT retransform / revalidate as no change to the underlying data (see screenshot to left)
9 | Delete all journal entries containing one of the 19 GL accounts to be moved with adjustments data. Navigate to Consol Actual Data Load Workflow --> Adj --> Unpost, Reject, & Delete. | Full JE inventory in Account Hierarchy Analysis sheet | Kristine
10 | Repost journals containing one of the 19 GL accounts with adjustments data |  | Kristine
| From the journals extract backup, create a clean journal file containing only the journals that uses the 19 GL accounts. | Files should be saved as .csv; Kristine has already created
Upload the created file in File Share under this path Applications > OneStreamProduction > Groups > Everyone > Journal_Posting
Navigate to Ally Journal Export dashboard in OnePlace and click on Import button
11 | Run Consolidation (Admin Tasks --> Consolidation) | For Consol Cube Re-Load | Kristine
Force Consolidate
Cube: Ally_Consol
Parent Filter: N/A; leave blank
Entity Filter: E#CO_20, E#CO_70
Consolidation Filter: C#USD
Scenario Filter: S#Actual
Time Filter: T#2019M12, T#2020M12, T#2021M12, T#2022M5
12 | Run Aggregation (Admin Tasks --> Ally_Expenses_Consol_Actual) | For Expense Cube Re-Load | Kristine
Consolidate
Cube: Ally_Expenses
Parent Filter: N/A; leave blank
Entity Filter: E#[Total CostCenters], E#CC_GF000001, E#CC_Core_BU
Consolidation Filter: C#Aggregated
Scenario Filter: S#Actual
| Time Filter: T#2020, T#2021, T#2022 | 2019 only used for Consol
13 | Verify the numbers |  | Kristine / Katherine
| Refresh data validation templates for 1 -2 months to ensure no variances / immaterial variances in consol actuals. | Prior to loading to Total Ally, Kristine to refresh 1-2 months of DV templates to confirm data refreshed to actuals as expected (e.g. Jan. 2020, May 2022). In later step, Ally to refresh templates (at least one per year) for further validation. | Kristine
Located in Consolidations Data Validation --> Validation Templates --> Associated time period. Download copy of each of the 4 templates and refresh (Legal Pre-Elim nonUSD, Legal Pre-Elim USD, Legal Post-Elim, Mgmt Post-Elim)
14 | Run Consol Actuals to Total Ally Planning integration for 2020M1 - 2022M5 & consolidate | *Dec. 2019 for consol ONLY; start at 2020 for Ally Total | Kristine
Set integration parameter boolean to manual
| Navigate to Ally_Total_ACT --> Ally_Total_Actual_Load Workflow Profile Load. Re-load the cube for each month for all the workflows except for Stat_Import. Can execute a bulk worfklow batch to "Load Cube" for all months in one year. | Do NOT retransform / revalidate as no change to the underlying data. Re-load Total_CCA, Total_PCA, Import_Consol_Topside, Import_Consol_Elims, Import_Consol_RE.
Run the data management step Consolidation_AllyConsol
Force Consolidate
Cube: Ally_Total
Parent Filter: N/A; leave blank
Entity Filter: E#PC_Total_Ally
Consolidation Filter: C#Aggregated
Scenario Filter: S#Actual
Time Filter: T#2020, T#2021, T#2022
15 | Verify the numbers |  | Katherine / Jeremy
| Refresh data validation templates for Dec. 2019, Dec. 2020, Dec. 2021, & Apr. 2022 to ensure no variances / immaterial variances. |  | Jeremy
| Review the Pre-Close & Post-Close Consolidation Cube Views |  | Katherine
| Refresh Consol to Total Ally Excel comparison as check for Total Ally |  | Katherine
16 | Run scripts to feed Actuals to Forecast scenarios using Seeding rule for Expense and Actual | Forecast data may need to be cleared first | Nidhi
Ally_Expense_Seed_Act2Forecast
Ally_Total_SeedAct2Forecast
17 | Aggregate 4_32 for 20221 - M4 in Ally Total & Ally Expense |  | Nidhi

## JE Approach
Approach | Est. Level of Effort (in Days) | Risks
(1) Move 166 accounts under To_Be_Deleted, rename with _old and create as new accounts under PlanningAccounts | 0.5
(2) Update Journals
Option A: Unpost, delete, and re-post all journal entries containing data for impacted accounts | 1 |  | *Selected Approach
(1) Determine list of journals containing data for any of these 166 accounts |  | - Risks around impacting the quality of already validated data
(2) Extract journal data using the PROD Journal Extract Dashboard & save copies
(3) Unpost & delete impacted JEs in OS PROD
(4) Repost journals containing one of the 19 GL accounts with adjustments data
From the journals extract backup, create a clean journal file containing only the journals that uses the 19 GL accounts.
Upload the created file in File Share under this path Applications > OneStreamProduction > Groups > Everyone > Journal_Posting
Navigate to Ally Journal Export dashboard in OnePlace and click on Import button
Option B: Create one JE per month to move data from orphaned _Old account to new Planning account | 1
(1) Use a quick view to extract intersections with adjustment data in _Old |  | - Need an additional journal every month to fix this issue - Would be a quick fix, with some clean ups required long term
(2) Create one JE per month to reclass balance from _Old account to actual account (which is now correctly in planning)
(3) Can correct data at a later point in time
Option C: Create Intermediate Parent in Planning | 1
(1) Create new member in Planning Account hierarchy to serve as intermediate parent |  | - Having intermediate parents b/w group accounts and operational accounts might cause some user confusion during reporting/analysis - Need to ensure the solution works with automated hierarchies feed from FDH and these intermediate parents do not cause data issues when moving across cubes/scenarios
(2) Move the 19 accounts with journals as children to the new intermediate parent
(3) Update the relationships in the transformation and integration logic
(3) Reload all data | 1
(4) Validate data | 2
TOTAL ESTIMATED EFFORT (using step 2 option A) | 4.5
TOTAL ESTIMATED EFFORT (using step 2 option B) | 4.5
TOTAL ESTIMATED EFFORT (using step 2 option C) | 4.5

## List of Accts w JEs
GL Accts. to be moved to Planning | 166 | Unique List of GL Accts. w/ JE data | 19 | Unique List of GL Accts. w/o JE data | 147
189030003 |  | 542011202 |  | 189030003
189030006 |  | 553010006 |  | 189030006
456700005 |  | 570120002 |  | 456700005
501140001 |  | 583001002 |  | 501140001
502030505 |  | 584010003 |  | 502030505
502030575 |  | 586011013 |  | 502030575
502030621 |  | 586021004 |  | 502030621
502030637 |  | 587010006 |  | 502030637
502030736 |  | 589010004 |  | 502030736
502030741 |  | 591010004 |  | 502030741
502031621 |  | 593010004 |  | 502031621
502031637 |  | 594010004 |  | 502031637
502021001 |  | 599990002 |  | 502021001
502020001 |  | 670010041 |  | 502020001
502090005 |  | 688501002 |  | 502090005
507060010 |  | 900000025 |  | 507060010
507060011 |  | 900000026 |  | 507060011
507060012 |  | 900000054 |  | 507060012
507060013 |  | 900000097 |  | 507060013
507060014 |  |  |  | 507060014
507060015 |  |  |  | 507060015
507060016 |  |  |  | 507060016
507060017 |  |  |  | 507060017
503000001 |  |  |  | 503000001
503000010 |  |  |  | 503000010
541010003 |  |  |  | 541010003
541010736 |  |  |  | 541010736
541011003 |  |  |  | 541011003
541021022 |  |  |  | 541021022
560010003 |  |  |  | 560010003
560010004 |  |  |  | 560010004
555040002 |  |  |  | 555040002
521002002 |  |  |  | 521002002
521002008 |  |  |  | 521002008
521003503 |  |  |  | 521003503
521003504 |  |  |  | 521003504
510900002 |  |  |  | 510900002
521003505 |  |  |  | 521003505
521003506 |  |  |  | 521003506
521003508 |  |  |  | 521003508
521003509 |  |  |  | 521003509
511010003 |  |  |  | 511010003
511010004 |  |  |  | 511010004
520101004 |  |  |  | 520101004
520101005 |  |  |  | 520101005
520101012 |  |  |  | 520101012
520103001 |  |  |  | 520103001
520103501 |  |  |  | 520103501
900000025 |  |  |  | 900000084
900000026 |  |  |  | 900000023
900000084 |  |  |  | 900000074
570120002 |  |  |  | 900000075
900000023 |  |  |  | 544001002
900000074 |  |  |  | 900000090
900000075 |  |  |  | 900000091
544001002 |  |  |  | 586041003
586011013 |  |  |  | 900000093
586021004 |  |  |  | 554010737
900000090 |  |  |  | 554010738
900000091 |  |  |  | 900000050
586041003 |  |  |  | 555010806
900000093 |  |  |  | 553010007
554010737 |  |  |  | 553010009
554010738 |  |  |  | 670020001
900000050 |  |  |  | 900000048
555010806 |  |  |  | 530801012
553010006 |  |  |  | 551090010
553010007 |  |  |  | 596010003
553010009 |  |  |  | 900000024
670020001 |  |  |  | 670040001
900000048 |  |  |  | 900000063
530801012 |  |  |  | 670040002
551090010 |  |  |  | 900000100
591010004 |  |  |  | 552010003
596010003 |  |  |  | 552010005
584010003 |  |  |  | 552010014
900000024 |  |  |  | 552010017
900000054 |  |  |  | 552010019
670040001 |  |  |  | 552010021
900000063 |  |  |  | 552010023
670040002 |  |  |  | 552010024
900000100 |  |  |  | 552010025
552010003 |  |  |  | 552010027
552010005 |  |  |  | 552010028
552010014 |  |  |  | 552010035
552010017 |  |  |  | 552010036
552010019 |  |  |  | 552010038
552010021 |  |  |  | 597030005
552010023 |  |  |  | 597030006
552010024 |  |  |  | 900000015
552010025 |  |  |  | 900000098
552010027 |  |  |  | 689801001
552010028 |  |  |  | 900000099
552010035 |  |  |  | 556020001
552010036 |  |  |  | 556010001
552010038 |  |  |  | 587010007
597030005 |  |  |  | 587010008
597030006 |  |  |  | 587010009
900000015 |  |  |  | 587010010
900000098 |  |  |  | 900000060
689801001 |  |  |  | 589010008
900000099 |  |  |  | 589010009
556020001 |  |  |  | 583001010
556010001 |  |  |  | 583001012
587010006 |  |  |  | 583001014
587010007 |  |  |  | 591010001
587010008 |  |  |  | 592010500
587010009 |  |  |  | 592010636
587010010 |  |  |  | 670010020
900000060 |  |  |  | 670010203
589010004 |  |  |  | 670019834
589010008 |  |  |  | 699999999
589010009 |  |  |  | 900000000
583001002 |  |  |  | 599990009
583001010 |  |  |  | 599990801
583001012 |  |  |  | 900000045
583001014 |  |  |  | 900000049
591010001 |  |  |  | 689500006
592010500 |  |  |  | 689500009
592010636 |  |  |  | 689500012
670010020 |  |  |  | 689500017
670010203 |  |  |  | 900000051
670019834 |  |  |  | 900000062
699999999 |  |  |  | 900000052
900000000 |  |  |  | 900000044
900000097 |  |  |  | 542011203
670010041 |  |  |  | 542011303
599990002 |  |  |  | 542021106
599990009 |  |  |  | 542021108
599990801 |  |  |  | 542012403
900000045 |  |  |  | 542012406
688501002 |  |  |  | 542012408
900000049 |  |  |  | 542012409
689500006 |  |  |  | 542012410
689500009 |  |  |  | 542021304
689500012 |  |  |  | 542021305
689500017 |  |  |  | 542022203
900000051 |  |  |  | 542022204
900000062 |  |  |  | 542022205
900000052 |  |  |  | 542022206
594010004 |  |  |  | 900000021
900000044 |  |  |  | 900000043
542011202 |  |  |  | 691010005
542011203 |  |  |  | 691010006
542011303 |  |  |  | 691010007
542021106 |  |  |  | 900000055
542021108 |  |  |  | 670010040
542012403
542012406
542012408
542012409
542012410
542021304
542021305
542022203
542022204
542022205
542022206
900000021
593010004
900000043
691010005
691010006
691010007
900000055
670010040